TO:  		Professor Bonnie Startt

FROM: 	Tiffany Sharp

DATE: 	February 26, 2012

SUBJECT:  	Progress Report

MAJOR HOME SECURITY SYSTEMS IN HAMPTON ROADS

WORK COMPLETED TO DATE

Feb 23:  Three security companies chosen to research:  ADT, Brinks, and Johns Brothers

Home Security

Feb 24:	Contact each home security company to request statistical information

Feb 25:  Formulate points/information to address

WORK IN PROGRESS

Feb 27:  Research equally divided among group members

Feb 27:  Independent research via Internet

WORK TO BE COMPLETED

Mar 18:  Collect and organize data

Mar 25:  Design layout and edit

Apr 1: 	Prepare for submission

DATE FOR COMPLETION:  April 29, 2012

| HOME SECURITY SYSTEMS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TASK | START DATE | DURATION (days) | DUE DATE |  |  |  |
| Form Group | 22-Feb | 2 | 24-Feb |  |  |  |  |
| Progress Report | 23-Feb | 3 | 26-Feb |  |  |  |  |
| Contact companies for information | 24-Feb | 7 | 2-Mar |  |  |  |  |
| Interview customers | 27-Feb | 13 | 11-Mar |  |  |  |  |
| Independent research via Internet | 27-Feb | 20 | 18-Mar |  |  |  |  |
| Collect and analyze data | 27-Feb | 20 | 18-Mar |  |  |  |  |
| Design layout and edit | 18-Mar | 7 | 25-Mar |  |  |  |  |
| Prepare rough draft | 25-Mar | 14 | 8-Apr |  |  |  |  |
| Submit final draft | 23-Apr | 6 | 29-Apr |  |  |  |  |